## Sheet1
Project Summary Costs
| Labor Total (Approximate) |  | 21388.5
| Furniture and Equipment |  | 77805
| Project Total (Approx) |  | 99193.5
Labor Costs |  | Hourly Rate
| Madhavi Kadam | 60
| Arjun Aditya | 45
| Tom Johansen | 44
| Samantha Peters | 48
| Isabella Cantina | 48
| Average | 49
|  | Time (hrs) | Hourly Rate | Approx. cost
Initiate Project
| Identifying stakeholders | 6 | 49 | 294
| Meeting with Stakeholders | 7 | 49 | 343
| Document Production | 4 | 49 | 196
Develop Project Charter
| Define Business Case | 1 | 49 | 49
| Define Project Scope | 1 | 49 | 49
Project Kickoff Meeting
| Meet in Conference Room | 1.5 | 49
| Conduct Site Survey | 2 | 49
Plan Project
| Design the Cubicle Furnitures to be installed | 8 | 49 | 392
| Design the Installation of VoIP handsets | 7 | 49 | 343
| Specify new Laptop Requirements | 7 | 49 | 343
| Specify Multifunctional printer-copier | 7 | 49 | 343
| Specify Ciena 7609 aggregation switch | 2 | 49 | 98
| Specify Cisco Aironet Wireless Access Points | 1.5 | 49 | 73.5
| Specify Cat 6e Cable | 2 | 49 | 98
| Procure the Cubicle Furnitures to be installed | 7 | 49 | 343
| Procure the Installation of VoIP Handsets | 7 | 49 | 343
| Procure New Laptops | 7 | 49 | 343
| Procure Multifunctional printer-copier | 7 | 49 | 343
| Procure Ciena 7609 aggregation switch | 4 | 49 | 196
| Procure Cisco Aironet Wireless Access Points | 4 | 49 | 196
| Procure Cat 6e Cable | 7 | 49 | 343
| Receive & Inspect Cubicle Furnitures | 5 | 49 | 245
| Receive & Inspect VoIP Handset | 10 | 49 | 490
| Receive & Inspect new Laptops | 10 | 49 | 490
| Receive & Inspect Multifunctional printer-copier | 10 | 49 | 490
| Receive & Inspect Ciena 7609 aggregation switch | 8 | 49
| Receive & Inspect Cisco Aironet Wireless Access Points | 8 | 49
| Receive and Inspect Cat 6e Cable | 12 | 49
Execute Project
| Install Cubicle Furniture | 16 | 49 | 784
| Install VoIP Handsets | 16 | 49 | 784
| Install New Laptops | 16 | 49 | 784
| Install Multifunctional Printer-Copier | 20 | 49 | 980
| Install Ciena 7609 aggregation switch | 8 | 49 | 392
| Install Cisco Aironet Wireless Access Points | 8 | 49 | 392
| Install Cat 6e Cable | 12 | 49 | 588
Test Project
| Test that the furniture is assembled | 20 | 49 | 980
| Test VoIP handset | 20 | 49 | 980
| Test New Laptops for Hardware | 15 | 49 | 735
| Test New Laptops for Software | 15 | 49 | 735
| Test printer-copier | 16 | 49 | 784
| Test Ciena 7609 Switch | 24 | 49 | 1176
| Test Cisco Aironet Wireless Access Points | 20 | 49 | 980
| Test Cat 6e Cable Connection | 16 | 49 | 784
Close Out Project
| Seak final approval from sponsors | 8 | 49 | 392
| Fix open items | 12 | 49 | 588
| Conduct survey with sponsors | 8 | 49 | 392
| Signing Off - Meeting | 8 | 49 | 392
| Create and Achieve Final Documentation | 8 | 49 | 392
| Ensure all vendor contracts are closed | 4 | 49 | 196
| Conduct training | 3 | 49 | 147
| Create user manuals | 8 | 49 | 392
| Reassigning resources | 4 | 49 | 196
| Labor Total (Approximate) | 468 | 2548 | 21388.5
| Labor Total (High) |  | 60 | 28080
| Labor Total (Low) |  | 44 | 20592
Equipment and Furniture Costs
|  | Number | Cost(each) | Total
| PC with Monitor & Software | 15 | 1850 | 27750
| VoIP Handsets | 15 | 525 | 7875
| Cubicle Furniture | 15 | 2225 | 33375
| Copier/Printer | 1 | 3950 | 3950
| Aironet Access Points | 6 | 340 | 2040
| Aggregation Switch | 1 | 2365 | 2365
| Network Cable | 1 | 450 | 450
| Equipment and Furniture Total |  |  | 77805